## Sheet1
2.0 RELEASE PLAN
Calculo de velocidad de equipo
SP Restantes | 71 | BackLog |  | SPRINT 1
Velocidad | 27 | US | SP | US | SP
SP Restantes | 3 | Emergency Button | 3 | Emergency Button | 3
|  | Integrate MasqueRouge with State Systems | 21 | Integrate MasqueRouge with State Systems | 21
|  | Follow up complaints (record calls and actions) | 8 | Investigation Android Implementation | 0
|  | [Mobile Android] App front page | 3 | Total SP | 24
|  | [Mobile Android] List Products | 5
|  | [Mobile Android] Filter and Search Products | 8 | SPRINT 2
|  | [Mobile Android] My Cart | 5 | US | SP
|  | [Mobile Android] Product Details | 5 | Follow up complaints (record calls and actions) | 8
|  | [Mobile Android] Complaint Forms(purchasing) | 8 | [Mobile Android] App front page | 3
|  | [Mobile Android]Emergency call integration | 5 | [Mobile Android] List Products | 5
|  | Total | 71 | [Mobile Android] Filter and Search Products | 8
|  |  |  | Total | 24
Beginning Date: November 4th
|  | Estimated 2nd Release Date: December 16th |  | SPRINT 3
|  |  |  | US | SP
|  |  |  | [Mobile Android] My Cart | 5
|  |  |  | [Mobile Android] Product Details | 5
|  |  |  | [Mobile Android] Complaint Forms(purchasing) | 8
|  |  |  | [Mobile Android]Emergency call integration | 5
|  |  |  | Total | 23